## Stories
ITG Solutions
Displaying 32 issues at 02/Jul/15 11:44 AM.
| Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Creator | Created | Last Viewed | Updated | Resolved | Due Date | Votes | Watchers | Images | Linked Issues | Description | Sprint | Epic Link | Daily.Priority | Rank
| ADSBPA-33 | As a user I would like to see the link the terms and conditions for use of the data. | Story | Closed | Major | Done | Mohammed Nauage | Phillip Armour | Phillip Armour | 2015-06-19 14:31 | 2015-06-20 09:50 | 2015-06-24 14:58 | 2015-06-22 20:58 | 2015-06-26 | 0 | 1 |  |  | As a user I would like to see the link the terms and conditions for use of the data. AC: display the url to the terms and conditions ( meta.disclaimer) | Sprint 1 | User Dashboard | 10 - Pending | 0¦i05snu:
| ADSBPA-39 | New Map Graphic | Story | Open | Major | Unresolved | Hiteshkumar N. Patel | Matthew Brown | Matthew Brown | 2015-06-22 20:59 | 2015-06-26 12:38 | 2015-06-26 12:38 |  |  | 0 | 6 |  |  | Replace the existing Google Map with a map that better illustrates the state-by-state level of the data in the API. AC: The map should be display information at the state level. AC: The map should allow individual state or combination of states be highlighted to convey the recall area for an enforcement action. AC: The map should display all 50 states as well as territories & protectorates (pending review of data). | Stretch |  | 10 - Pending | 0¦i05t71:
| ADSBPA-36 | As a user I want to see the full details for the enforcement report I select from search results. | Story | Closed | Major | Done | Kevin S. Foglio | Phillip Armour | Phillip Armour | 2015-06-19 14:33 | 2015-06-27 10:02 | 2015-06-27 10:13 | 2015-06-24 10:25 | 2015-06-26 | 0 | 2 | _thumb_62332.png | ADSBPA-64, ADSBPA-61 | As a user I want to see detailed enforcement reports for cases near me. AC: I can see a pop-up with full information about the enforcement reports based on my city/state. | Sprint 1 | User Dashboard | 10 - Pending | 0¦i05snu:v
| ADSBPA-35 | As a user I would like to see the current status of food enforcement reports (“recalls”) in my general vicinity. | Story | In Progress | Major | Unresolved | Mohammed Nauage | Phillip Armour | Phillip Armour | 2015-06-19 14:32 | 2015-07-02 11:40 | 2015-06-27 10:23 |  | 2015-06-26 | 0 | 1 |  |  | As a user I would like to see the current status of food enforcement reports (“recalls”) in my general vicinity. AC: I have the ability to enter a zip code (or use location services in browser) AC: I am able to see a visual representation of “risk” as computed from quantity, severity, reports, status | Stretch | User Dashboard | 10 - Pending | 0¦i05t72:i
| ADSBPA-32 | As a user I would like to see the data set I am searching was last updated | Story | Closed | Major | Fixed | Hiteshkumar N. Patel | Phillip Armour | Phillip Armour | 2015-06-19 14:31 | 2015-06-27 10:09 | 2015-06-30 11:21 | 2015-06-29 17:38 | 2015-06-26 | 0 | 2 | _thumb_62296.png _thumb_62371.png |  | As a user I would like to see the data set I am searching was last updated. AC: display the last update date (meta.last_updated) | Sprint 1 | User Dashboard | 10 - Pending | 0¦i05snt:
| ADSBPA-37 | As a user, I need to be able to search food recall data with various search fields so that I can better understand food recall enforcement reports. | Story | Closed | Major | Fixed | Phillip Armour | Phillip Armour | Phillip Armour | 2015-06-19 14:34 | 2015-07-01 13:11 | 2015-07-01 15:06 | 2015-07-01 15:06 | 2015-06-26 | 0 | 4 |  | ADSBPA-49, ADSBPA-40 | As a user, I need to be able to search food recall data with various search fields so that I can better understand food recall enforcement reports. AC: I am able to search by City and see associated results AC: I am able to search by State and see associated results AC: I am able to search by Associated Company and see associated results AC: I am able to search by Recall Date Range and see associated results AC: I am able to search by keywords in the Reason for Recall and see associated results AC: I am able to enter one or more search criteria (from the above) - assume AND AC: At least 1 search criteria must be entered or else the user is notified | Sprint 1 | User Dashboard | 10 - Pending | 0¦i05snu:x
| ADSBPA-34 | As a user I should be made aware that search results for data prior to 2012 may be incomplete. | Story | Closed | Major | Fixed | Hiteshkumar N. Patel | Phillip Armour | Phillip Armour | 2015-06-19 14:32 | 2015-06-27 10:04 | 2015-07-01 15:06 | 2015-07-01 15:06 | 2015-06-26 | 0 | 2 |  | ADSBPA-48, ADSBPA-62 | As a user I should be made aware that search results for data prior to 2012 may be incomplete. AC: display a warning with the search results to clarify for user. AC: require affirmative acknowledgement in the form of a click. | Sprint 1 | User Dashboard | 10 - Pending | 0¦i05snu:i
| ADSBPA-50 | As a user I would like to see count of new records for each search | Story | Closed | Minor | Done | Kevin S. Foglio | Matthew Brown | Matthew Brown | 2015-06-23 14:53 | 2015-06-24 12:40 | 2015-06-25 13:56 | 2015-06-24 20:01 |  | 0 | 3 |  |  | Show above search restuls | Sprint 1 |  | 10 - Pending | 0¦i05sny:zwzx
| ADSBPA-43 | As a user I would like to see where can I go to return the item | Story | Open | Minor | Unresolved | Matthew Brown | Matthew Brown | Matthew Brown | 2015-06-23 14:49 | 2015-06-23 23:34 | 2015-06-27 10:22 |  |  | 0 | 4 |  |  | As a user I would like to see vendors around me that will accept a return or know how I return the item to a manufacturer | Stretch |  | 10 - Pending | 0¦i05t72:
| ADSBPA-44 | As a user I would like to see an an image for each food item | Story | Open | Minor | Unresolved | Mohammed Nauage | Matthew Brown | Matthew Brown | 2015-06-23 14:50 | 2015-06-26 15:11 | 2015-06-27 10:22 |  |  | 0 | 6 |  |  |  | Stretch |  | 10 - Pending | 0¦i05t71:i
| ADSBPA-67 | Add style for home page | Story | Closed | Minor | Fixed | Tito Araujo | Phillip Armour | Phillip Armour | 2015-06-27 10:16 | 2015-06-27 10:17 | 2015-07-01 15:06 | 2015-07-01 15:06 |  | 0 | 1 |  |  | Change the image to be full width and perform parallax effect when the user scrolls down. Add better formatting to the existing links back to OpenFDA (the headers, links, etc.) | Sprint 1 |  | 10 - Pending | 0¦i05sny:zwzzzy
| ADSBPA-42 | As a user I would like the top menu to be a Nav Bar | Story | Closed | Minor | Fixed | Tito Araujo | Matthew Brown | Matthew Brown | 2015-06-23 14:49 | 2015-06-23 23:25 | 2015-07-01 15:05 | 2015-07-01 15:05 |  | 0 | 6 |  |  |  | Sprint 1 |  | 10 - Pending | 0¦i05snu:w
| ADSBPA-57 | As a user I would like to be able to export search results to common formats (CSV, XLS, etc.) | Story | Closed | Minor | Fixed | Unassigned | Matthew Brown | Matthew Brown | 2015-06-23 14:57 |  | 2015-07-01 15:06 | 2015-07-01 15:06 |  | 0 | 1 |  |  |  | Sprint 1 |  | 10 - Pending | 0¦i05sny:zwzzzzi
| ADSBPA-41 | As a user I would like to be able to see a timeline of the recall | Story | Closed | Minor | Fixed | Matthew Brown | Matthew Brown | Matthew Brown | 2015-06-23 14:49 | 2015-06-24 10:31 | 2015-07-01 15:15 | 2015-07-01 15:15 |  | 0 | 5 |  |  | Display a graphical representation for the dates associated with a recall. | Sprint 1 |  | 10 - Pending | 0¦i05sny:zwzzl
| ADSBPA-58 | As a user I would like to see the 5 most recent enforcement reports for my location when the page loads | Story | Closed | Minor | Done | Mohammed Nauage | Matthew Brown | Matthew Brown | 2015-06-23 14:58 | 2015-06-25 19:37 | 2015-07-01 15:28 | 2015-06-29 00:21 |  | 0 | 3 | _thumb_62386.png |  |  | Sprint 1 |  | 10 - Pending | 0¦i05sny:zwzzk
| ADSBPA-56 | As a user I would roll-over text for for 508 compliance | Story | Closed | Minor | Fixed | Unassigned | Matthew Brown | Matthew Brown | 2015-06-23 14:57 |  | 2015-07-01 15:16 | 2015-07-01 15:16 |  | 0 | 1 |  |  |  | Sprint 1 |  | 10 - Pending | 0¦i05sny:zwzzzz
| ADSBPA-66 | Navigation and Header Bar | Story | Closed | Minor | Fixed | Hiteshkumar N. Patel | Phillip Armour | Phillip Armour | 2015-06-27 10:13 | 2015-06-27 10:13 | 2015-07-01 16:53 | 2015-06-30 13:03 | 2015-06-29 | 0 | 1 |  |  | As discussed, Please revise the header to be a solid color and stretch the width of the screen (100%). We also want to incorporate the home page such that, we add the image and search box. Searching would take you to the results page. Clicking the logo would take you back to the home page. Also add the "general" search input to the form on the search results page and only show the advanced form (without an option to toggle back to basic). | Sprint 1 |  | 10 - Pending | 0¦i05sny:zwzzzi
| ADSBPA-68 | Change logo to support green background | Story | Closed | Minor | Fixed | Tito Araujo | Phillip Armour | Phillip Armour | 2015-06-27 10:18 | 2015-07-02 11:41 | 2015-07-01 16:53 | 2015-06-30 10:13 |  | 0 | 2 |  |  | as discussed, Please convert the logo elements from green to white to accommodate a green background (for the header). Review how blank and other things look against the green. And change accent colors from blue to something else (i.e. red/orange/whatever?). | Sprint 1 |  | 10 - Pending | 0¦i05sny:zwzzzx
| ADSBPA-59 | As a user I would like a google-stye omni-bar search field for free text searching | Story | Closed | Minor | Fixed | Phillip Armour | Matthew Brown | Matthew Brown | 2015-06-23 14:59 | 2015-06-24 10:20 | 2015-07-01 16:53 | 2015-06-30 13:02 |  | 0 | 1 |  | ADSBPA-60 |  | Sprint 1 |  | 10 - Pending | 0¦i05sny:zwzw
| ADSBPA-47 | As a user I would like to be able to sort search results | Story | Closed | Minor | Done | Mohammed Nauage | Matthew Brown | Matthew Brown | 2015-06-23 14:51 | 2015-06-25 21:03 | 2015-07-01 16:57 | 2015-06-29 00:19 |  | 0 | 6 |  |  |  | Sprint 1 |  | 10 - Pending | 0¦i05sny:zwzzm
| ADSBPA-20 | a. assigned one leader | Story | Closed | Critical | Fixed | Sudha Venkateswaran | Phillip Armour | Phillip Armour | 2015-06-19 14:19 | 2015-06-26 15:46 | 2015-06-23 13:48 | 2015-06-23 13:47 | 2015-06-26 | 0 | 2 |  |  | a. assigned one leader, gave that person authority and responsibility and held that person accountable for the quality of the prototype submitted | Sprint 1 | Digital Services Playbook | 10 - Pending | 0¦i05snv:
| ADSBPA-21 | b. assembled a multidisciplinary and collaborative team | Story | Closed | Critical | Fixed | Sudha Venkateswaran | Phillip Armour | Phillip Armour | 2015-06-19 14:20 | 2015-06-27 09:35 | 2015-07-01 16:52 | 2015-06-27 09:35 | 2015-06-26 | 0 | 3 |  |  | b. assembled a multidisciplinary and collaborative team that includes at a minimum two of the labor categories limited to the Development Pool labor categories to develop the prototype as quoted in Attachment C. The quoter’s proposed mix of labor categories and level of effort for its working prototype, as reflected in Attachment C, shall be evaluated to assess the quoter’s understanding and capability to supply agile delivery services Shred document is here: https://docs.google.com/document/d/1gZeyC-9Za6k7ia2ENN6lOnLoNaPrRbwWrfoX8xrlci4/edit | Sprint 1 | Digital Services Playbook | 10 - Pending | 0¦i05snx:
| ADSBPA-22 | c. used at least five modern and open-source technologies | Story | Closed | Critical | Fixed | Phillip Armour | Phillip Armour | Phillip Armour | 2015-06-19 14:21 | 2015-06-26 17:13 | 2015-07-01 16:52 | 2015-06-23 15:05 | 2015-06-26 | 0 | 4 |  |  | c. used at least five modern and open-source technologies, regardless of architectural layer (frontend, backend etc) Shred document: https://docs.google.com/document/d/15zhEu4_eENvgwp13lS-SYvIZEMz37YrT7ITSED-Dpe0/edit | Sprint 1 | Digital Services Playbook | 10 - Pending | 0¦i05sny:
| ADSBPA-23 | d. deployed the prototype on an Infrastructure as a Service (IaaS) or Platform as a Service (PaaS) provider | Story | Closed | Critical | Fixed | Phillip Armour | Phillip Armour | Phillip Armour | 2015-06-19 14:22 | 2015-07-01 12:51 | 2015-07-01 16:53 | 2015-07-01 12:51 | 2015-06-26 | 0 | 2 |  |  | d. deployed the prototype on an Infrastructure as a Service (IaaS) or Platform as a Service (PaaS) provider, and indicated which provider was used Shred document: https://docs.google.com/document/d/1micWOlOxuMa4GmK386Nwi36RZY-rzq_Jle0m5_0iouQ/edit | Sprint 1 | Digital Services Playbook | 10 - Pending | 0¦i05sny:xi
| ADSBPA-24 | e. wrote unit tests for their code | Story | Closed | Critical | Fixed | Phillip Armour | Phillip Armour | Phillip Armour | 2015-06-19 14:23 | 2015-07-01 12:52 | 2015-07-01 16:53 | 2015-07-01 12:52 | 2015-06-26 | 0 | 4 |  |  | e. wrote unit tests for their code Shred document: https://docs.google.com/document/d/1ScJWsY6SJ3_ym463rWahVis8jbmrlcwHnpQIesa7HLg/edit | Sprint 1 | Digital Services Playbook | 10 - Pending | 0¦i05sny:xd
| ADSBPA-25 | f. set up or used a continuous integration system | Story | Closed | Critical | Fixed | Phillip Armour | Phillip Armour | Phillip Armour | 2015-06-19 14:24 | 2015-07-01 12:51 | 2015-07-01 16:52 | 2015-07-01 12:51 | 2015-06-26 | 0 | 2 |  |  | f. set up or used a continuous integration system to automate the running of tests and continuously deployed their code to their IaaS or PaaS provider Shred document is here: https://docs.google.com/document/d/1ZlLFKDIDpEeAnmN-GWK-lJjhrRfH9zGD7zNRXbkRPLM/edit | Sprint 1 | Digital Services Playbook | 10 - Pending | 0¦i05sny:x9
| ADSBPA-26 | g. set up or used configuration management | Story | Closed | Critical | Fixed | Phillip Armour | Phillip Armour | Phillip Armour | 2015-06-19 14:24 | 2015-07-01 12:51 | 2015-07-01 16:52 | 2015-07-01 12:51 | 2015-06-26 | 0 | 3 |  |  | g. set up or used configuration management Shred document: https://docs.google.com/document/d/1c5uWTMMKG2tRl8Pdb90mMjCv7t3Z1CGTXS_V2KkD304/edit | Sprint 1 | Digital Services Playbook | 10 - Pending | 0¦i05sny:x
| ADSBPA-27 | h. set up or used continuous monitoring | Story | Closed | Critical | Fixed | Phillip Armour | Phillip Armour | Phillip Armour | 2015-06-19 14:24 | 2015-07-01 12:51 | 2015-07-01 16:53 | 2015-07-01 12:51 | 2015-06-26 | 0 | 4 |  |  | h. set up or used continuous monitoring Shred doc: https://docs.google.com/document/d/1lpL7Q6V299USD5JesmFy-Iz8NtJ-I_V4EZc-pZ0wASw/edit | Sprint 1 | Digital Services Playbook | 10 - Pending | 0¦i05sny:y
| ADSBPA-28 | i. deploy their software in a container | Story | Closed | Critical | Fixed | Phillip Armour | Phillip Armour | Phillip Armour | 2015-06-19 14:25 | 2015-07-01 12:52 | 2015-07-01 16:54 | 2015-07-01 12:52 | 2015-06-26 | 0 | 3 |  |  | i. deploy their software in a container (i.e., utilized operating-system-level virtualization) Shred document: https://docs.google.com/document/d/1b-5jap1g4uyyvlP_ppdexEOb8azNQ_45aM69uR9nu2k/edit | Sprint 1 | Digital Services Playbook | 10 - Pending | 0¦i05sny:zm
| ADSBPA-29 | j. used an interactive approach | Story | Closed | Critical | Fixed | Phillip Armour | Phillip Armour | Phillip Armour | 2015-06-19 14:26 | 2015-06-29 13:15 | 2015-06-30 13:02 | 2015-06-30 13:02 | 2015-06-26 | 0 | 4 |  |  | j. used an interactive approach, where feedback informed subsequent work or versions of the prototype Shred document: https://docs.google.com/document/d/1iXNBTmacO-CdBE0TdzkcM6WVm5eHrjX3wKXHotrrudU/edit | Sprint 1 | Digital Services Playbook | 10 - Pending | 0¦i05sny:zi
| ADSBPA-30 | k. provided sufficient documentation | Story | Closed | Critical | Fixed | Phillip Armour | Phillip Armour | Phillip Armour | 2015-06-19 14:26 | 2015-06-29 13:16 | 2015-06-30 13:03 | 2015-06-30 13:03 | 2015-06-26 | 0 | 3 |  |  | k. provided sufficient documentation to install and run their prototype on another machine Shred doc is here: https://docs.google.com/document/d/1eekoiJrI0U4ctaI6dKSozuBLTHgUEHZhzpCT0qyVlRs/edit | Sprint 1 | Digital Services Playbook | 10 - Pending | 0¦i05sny:zr
| ADSBPA-31 | l. prototype and underlying platforms used to create and run the prototype are openly licensed and free of charge | Story | Closed | Critical | Fixed | Sudha Venkateswaran | Phillip Armour | Phillip Armour | 2015-06-19 14:27 | 2015-07-01 12:52 | 2015-07-01 16:56 | 2015-07-01 12:52 | 2015-06-26 | 0 | 2 |  |  | l. prototype and underlying platforms used to create and run the prototype are openly licensed and free of charge Shred doc is here: https://docs.google.com/document/d/1W2Y9z2KVnvJxqJw3a2mQ60Da0BmAbNznnXVFQmMRGcM/edit | Sprint 1 | Digital Services Playbook | 10 - Pending | 0¦i05sny:zv
Generated at Thu Jul 02 11:44:07 EDT 2015 by Phillip Armour using JIRA 6.3.9#6339-sha1:46fa26140bf81c66e10e6f784903d4bfb1a521ae.