## Stories
ITG Solutions
Displaying 18 issues
| Key | Summary | Issue Type | Description | Sprint | Epic Link | Story Points | Status | Priority | Resolution | Assignee
| ADSBPA-32 | As a user I would like to see the data set I am searching was last updated | Story | As a user I would like to see the data set I am searching was last updated. AC: display the last update date (meta.last_updated) | Sprint 1 | User Dashboard | 1 | Open | Major | Unresolved | Hiteshkumar N. Patel
| ADSBPA-33 | As a user I would like to see the link the terms and conditions for use of the data. | Story | As a user I would like to see the link the terms and conditions for use of the data. AC: display the url to the terms and conditions ( meta.disclaimer) | Sprint 1 | User Dashboard | 1 | Open | Major | Unresolved | Mohammed Nauage
| ADSBPA-34 | As a user I should be made aware that search results for data prior to 2012 may be incomplete. | Story | As a user I should be made aware that search results for data prior to 2012 may be incomplete. AC: display a warning with the search results to clarify for user. AC: require affirmative acknowledgement in the form of a click. | Sprint 1 | User Dashboard | 1 | Open | Major | Unresolved | Hiteshkumar N. Patel
| ADSBPA-35 | As a user I would like to see the current status of food enforcement reports (“recalls”) in my general vicinity. | Story | As a user I would like to see the current status of food enforcement reports (“recalls”) in my general vicinity. AC: I have the ability to enter a zip code (or use location services in browser) AC: I am able to see a visual representation of “risk” as computed from quantity, severity, reports, status | Sprint 1 | User Dashboard | 4 | Open | Major | Unresolved | Mohammed Nauage
| ADSBPA-36 | As a user I want to see the full details for the enforcement report I select from search results. | Story | As a user I want to see detailed enforcement reports for cases near me. AC: I can see a pop-up with full information about the enforcement reports based on my city/state. | Sprint 1 | User Dashboard | 2 | Open | Major | Unresolved | Kevin S. Foglio
| ADSBPA-37 | As a user, I need to be able to search food recall data with various search fields so that I can better understand food recall enforcement reports. | Story | As a user, I need to be able to search food recall data with various search fields so that I can better understand food recall enforcement reports. AC: I am able to search by City and see associated results AC: I am able to search by State and see associated results AC: I am able to search by Associated Company and see associated results AC: I am able to search by Recall Date Range and see associated results AC: I am able to search by keywords in the Reason for Recall and see associated results AC: I am able to enter one or more search criteria (from the above) - assume AND AC: At least 1 search criteria must be entered or else the user is notified | Sprint 1 | User Dashboard | 4 | Open | Major | Unresolved | Phillip Armour
| ADSBPA-20 | a. assigned one leader | Story | a. assigned one leader, gave that person authority and responsibility and held that person accountable for the quality of the prototype submitted | Sprint 1 | Digital Services Playbook | 1 | Open | Critical | Unresolved | Sudha Venkateswaran
| ADSBPA-21 | b. assembled a multidisciplinary and collaborative team | Story | b. assembled a multidisciplinary and collaborative team that includes at a minimum two of the labor categories limited to the Development Pool labor categories to develop the prototype as quoted in Attachment C. The quoter’s proposed mix of labor categories and level of effort for its working prototype, as reflected in Attachment C, shall be evaluated to assess the quoter’s understanding and capability to supply agile delivery services Shred document is here: https://docs.google.com/document/d/1gZeyC-9Za6k7ia2ENN6lOnLoNaPrRbwWrfoX8xrlci4/edit | Sprint 1 | Digital Services Playbook | 1 | Open | Critical | Unresolved | Sudha Venkateswaran
| ADSBPA-22 | c. used at least five modern and open-source technologies | Story | c. used at least five modern and open-source technologies, regardless of architectural layer (frontend, backend etc) Shred document: https://docs.google.com/document/d/15zhEu4_eENvgwp13lS-SYvIZEMz37YrT7ITSED-Dpe0/edit | Sprint 1 | Digital Services Playbook | 1 | Open | Critical | Unresolved | Phillip Armour
| ADSBPA-23 | d. deployed the prototype on an Infrastructure as a Service (IaaS) or Platform as a Service (PaaS) provider | Story | d. deployed the prototype on an Infrastructure as a Service (IaaS) or Platform as a Service (PaaS) provider, and indicated which provider was used Shred document: https://docs.google.com/document/d/1micWOlOxuMa4GmK386Nwi36RZY-rzq_Jle0m5_0iouQ/edit | Sprint 1 | Digital Services Playbook | 4 | Open | Critical | Unresolved | Phillip Armour
| ADSBPA-24 | e. wrote unit tests for their code | Story | e. wrote unit tests for their code Shred document: https://docs.google.com/document/d/1ScJWsY6SJ3_ym463rWahVis8jbmrlcwHnpQIesa7HLg/edit | Sprint 1 | Digital Services Playbook | 2 | Open | Critical | Unresolved | Phillip Armour
| ADSBPA-25 | f. set up or used a continuous integration system | Story | f. set up or used a continuous integration system to automate the running of tests and continuously deployed their code to their IaaS or PaaS provider Shred document is here: https://docs.google.com/document/d/1ZlLFKDIDpEeAnmN-GWK-lJjhrRfH9zGD7zNRXbkRPLM/edit | Sprint 1 | Digital Services Playbook | 2 | Open | Critical | Unresolved | Phillip Armour
| ADSBPA-26 | g. set up or used configuration management | Story | g. set up or used configuration management Shred document: https://docs.google.com/document/d/1c5uWTMMKG2tRl8Pdb90mMjCv7t3Z1CGTXS_V2KkD304/edit | Sprint 1 | Digital Services Playbook | 2 | Open | Critical | Unresolved | Phillip Armour
| ADSBPA-27 | h. set up or used continuous monitoring | Story | h. set up or used continuous monitoring Shred doc: https://docs.google.com/document/d/1lpL7Q6V299USD5JesmFy-Iz8NtJ-I_V4EZc-pZ0wASw/edit | Sprint 1 | Digital Services Playbook | 4 | Open | Critical | Unresolved | Phillip Armour
| ADSBPA-28 | i. deploy their software in a container | Story | i. deploy their software in a container (i.e., utilized operating-system-level virtualization) Shred document: https://docs.google.com/document/d/1b-5jap1g4uyyvlP_ppdexEOb8azNQ_45aM69uR9nu2k/edit | Sprint 1 | Digital Services Playbook | 2 | Open | Critical | Unresolved | Phillip Armour
| ADSBPA-29 | j. used an interactive approach | Story | j. used an interactive approach, where feedback informed subsequent work or versions of the prototype Shred document: https://docs.google.com/document/d/1iXNBTmacO-CdBE0TdzkcM6WVm5eHrjX3wKXHotrrudU/edit | Sprint 1 | Digital Services Playbook | 1 | Open | Critical | Unresolved | Phillip Armour
| ADSBPA-30 | k. provided sufficient documentation | Story | k. provided sufficient documentation to install and run their prototype on another machine Shred doc is here: https://docs.google.com/document/d/1eekoiJrI0U4ctaI6dKSozuBLTHgUEHZhzpCT0qyVlRs/edit | Sprint 1 | Digital Services Playbook | 2 | Open | Critical | Unresolved | Phillip Armour
| ADSBPA-31 | l. prototype and underlying platforms used to create and run the prototype are openly licensed and free of charge | Story | l. prototype and underlying platforms used to create and run the prototype are openly licensed and free of charge Shred doc is here: https://docs.google.com/document/d/1W2Y9z2KVnvJxqJw3a2mQ60Da0BmAbNznnXVFQmMRGcM/edit | Sprint 1 | Digital Services Playbook | 1 | Open | Critical | Unresolved | Sudha Venkateswaran